## 01 - Onboarding
Requirement ID # | Testcase # | Test Scenarios | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Status | Status (19-feb)
| o1 | User should be able to see the onboarding screens after launching the mobile app fro the first time. | Application should be installed on the users device. | User launches a mobile application form the android/ios device. |  | Applicaiton should get launched and user should be able to see the welcome screen. | Applicaiton should get launched and user should be able to see the welcome screen. | Pass | Pass
| o2 | Verify that user should be seeing the 1st page of onboarding containing all the required elements. | o1 | User clicks on the Get Started button. |  | Screen should appear to user with following elements : 1. Ahhaa logo. 2. A greeting title 'Welcome to Ahhaa' 3. A sub title 'Your wellbeing partner !' 4. A Get started button. | Screen should appear to user with following elements : 1. Ahhaa logo. 2. A greeting title 'Welcome to Ahhaa' 3. A sub title 'Your wellbeing partner !' 4. A Get started button. | Pass | Pass
| o3 | Verify that user should be seeing the 2nd page of onboarding containing all the required elements. | o2 | User clicks on the next button. |  | Screen should appear to user with following elements : 1. Logo graphics 2. A screen title 'Keep calm and stay in control' 3. A sub title 'Learn, breath, set daily goals.' 4. Progress bar with info of current page and upcoming pages. 5. A button with a text 'Next'. | Screen should appear to user with following elements : 1. Logo graphics 2. A screen title 'Keep calm and stay in control' 3. A sub title 'Learn, breath, set daily goals.' 4. Progress bar with info of current page and upcoming pages. 5. A button with a text 'Next'. | Pass | Pass
| o4 | Verify that user should be seeing the 3rd page of onboarding containing all the required elements. | o3 | User clicks on the next button. |  | Screen should appear to user with following elements : 1. Logo graphics 2. A screen title 'Personalize your plans with ease' 3. A sub title 'Set schedule as per your needs' 4. Progress bar with info of current page and upcoming pages. 5. A button with a text 'Next'. | Screen should appear to user with following elements : 1. Logo graphics 2. A screen title 'Personalize your plans with ease' 3. A sub title 'Set schedule as per your needs' 4. Progress bar with info of current page and upcoming pages. 5. A button with a text 'Next'. | Pass | Pass
| o5 | Verify that user should be seeing the 4th page of onboarding containing all the required elements. | o4 | User clicks on the next button. |  | Screen should appear to user with following elements : 1. Logo graphics 2. A screen title 'Meet your wellness guide' 3. A sub title 'Chat, get health tips & stay motivated.' 4. Progress bar with info of current page and upcoming pages. 5. A button with a text 'Next'. | Screen should appear to user with following elements : 1. Logo graphics 2. A screen title 'Meet your wellness guide' 3. A sub title 'Chat, get health tips & stay motivated.' 4. Progress bar with info of current page and upcoming pages. 5. A button with a text 'Next'. | Pass | Pass
| o6 | Verify that user should be seeing the login page providing options as login as an individual or organizaion. | o5 |  |  | Screen should appear to user with following elements : 1. A screen title 'Login As' 2. A sub title 'Let's start your wellbeing journey.' 3. Button labeled as 'Individual' 4. Button labeled as 'Organization' | Screen should appear to user with following elements : 1. A screen title 'Login As' 2. A sub title 'Let's start your wellbeing journey.' 3. Button labeled as 'Individual' 4. Button labeled as 'Organization' | Pass | Pass
| o7 | Verify that user should be able to skip the on boarding by clicking on the skip intro button. | o1 | User clicks on the skip into button. |  | User should get ridirected to Login As page , provided with an option to login as an individual or organization. | not functional | Failed | Pass

## 02 - Signup
Requirement ID # | Testcase # | Test Scenarios | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Status (19-feb)
2.1 | s1 | Verify that user should be albe to land on the signup page. | t7 (login testcase) | 1. Tap on Signup link from the login page. |  | User should be able to redirect ot the Signup page. |  | Passed
2.1 | s2 | Verify that user should be able to see all the required fields, links and buttons. | s1 | User be on Sign up page. |  | User should be able to see the following elements : 1. Page titled 'Create an account'. 2. Input field with title 'Name', icon and placeholder 'Enter your name'. 3. Input field with title 'Email', icon and placeholder 'Enter your email'. 4. Input field with title 'Password', icon and placeholder 'Enter your password'. 5. A check box. 6. Privacy Policy and Terms of use link. 7. Login , link 8. Google, facebook, instagram and signup buttons. | User should be able to see the following elements : 1. Page titled 'Create an account'. 2. Input field with title 'Name', icon and placeholder 'Enter your name'. 3. Input field with title 'Email', icon and placeholder 'Enter your email'. 4. Input field with title 'Password', icon and placeholder 'Enter your password'. 5. A check box. 6. Privacy Policy and Terms of use link. 7. Login , link 8. Google, facebook, instagram and signup buttons. | Passed
2.1 | s3 | Verify user signup with empty fields. | s2 | 1. Tap on sign up button, leaving all the fields as empty. | Full Name : Email : Password : | It should prompt error messages for empty fields. User should not be able to signup successfully. | Error messages prompted | Passed
2.1 | s4 | Verify user signup with valid full name and empty email and empty password. | s2 | 1. User tap on full name input field and enters data. 2. User clicks on the signup button, leaving email, password and checkbox checked/empty. | Full Name : neil conner Email : Password : | It should prompt error messages for empty fields. User should not be able to signup successfully. | Error messages prompted | Passed
2.1 | s5 | Verify user signup with valid full name and valid email and empty password. | s2 | 1. User taps on full name input field and enters data. 2. User taps on email input field and enters an email address. 3. User clicks on the signup button, leaving password and checkbox checked/empty. | Full Name : neil conner Email : neilconner@gmail.com Password : | It should prompt error messages for empty fields. User should not be able to signup successfully. | Error messages prompted | Passed
2.1 | s6 | Verify user signup with empty full name and valid email and valid password. | s2 | 1. User taps on email input field and enters data. 2. User taps on password input field and enters a password. 3. User clicks on the signup button, leaving full name and checkbox checked/empty. | Full Name : Email : neilconner@gmail.com Password : testing123 | It should prompt error messages for empty fields. User should not be able to signup successfully. | Error messages prompted | Passed
2.1 | s7 | Verify user signup with invalid data format for full name, email address and password policy. | s2 | 1. User taps on full name input field and enters invalid format data. 2. User taps on email input field and enters invalid format email. 3. User taps on password field and enters invalid format password. 4. User clicks on the signup button and leaving the checkbox as checked/empty. | Full Name : 123434 Email : neilconner%gmail.com Password : 123465484 | It should prompt error messages for empty fields. User should not be able to signup successfully. | Error messages prompted | Passed
2.1 | s8 | Verify user is able to redirect to login screen by clicking on Login link. | s2 | 1. User clicks on the login link. |  | It should redirect the user on the login page successfully. | Redirects to the success screen leading to home screen. | Passed
2.1 | s9 | Verify privacy policy and term of use link to be functional. | s2 | 1. User clicks on the privacy policy link. |  | It should prompt a privacy policy screen PDF screen. | pdf opened with terms and conditions. | Passed
2.1 | s10 | Verify user signup without checkin or without accepting privacy policy. | s2 | 1. User taps on full name input field and enters a valid full name. 2. User taps on email input field and enters a valid email address. 3. User taps on password input field and enters a valid password. 4. User leaves the checkbox as empty . 5. User taps on the signup button. | Full Name : neil conner Email : neilconner@gmail.com Password : testing123 | It should prompt an error message about the unchecked box. | Error messages prompted | Passed
2.1 | s11 | Verify user signup with checkin or with accepting privacy policy | s2 | 1. User taps on full name input field and enters a valid full name. 2. User taps on email input field and enters a valid email address. 3. User taps on password input field and enters a valid password. 4. User taps the checkbox. 5. User taps on the signup button. | Full Name : neil conner Email : neilconner@gmail.com Password : testing123 | User should be able to signup successfully. | User got succussfully signedup and redirected to the dashboard. | Passed
2.2 | s12 | Verify user signup with Google account | s2 | User taps on the Google account icon. |  | user should be ablt to signup with their google account successfully. | Not functional | Failed
2.2 | s13 | Verify user signup with Facebook account. | s2 | User taps on the Facebook account icon. |  | user should be ablt to signup with their Facebook account successfully. | Not functional | Failed
2.2 | s14 | Verify user signup with Instagram account | s2 | User taps on the Instagram account icon. |  | user should be ablt to signup with their Instagram account successfully. | Not functional | Failed
2.1 | s15 | Verify the hide icon can hide/unhide the password written in the password field. | s2 | 1. User taps on password input field and enters data. 2. User taps on the hide/unhide button |  | User should be able to see the text as masked and unmasked. | Functional | Passed
2.1 | s16 | Verifty user sign up with all vaild credentials in ofline mode. | s2 | Device is not connected to network. 1. User taps on full name input field and enters a valid full name. 2. User taps on email input field and enters a valid email address. 3. User taps on password input field and enters a valid password. 4. User taps the checkbox. 5. User taps on the signup button. | Full Name : neil conner Email : neilconner@gmail.com Password : testing123 | It should prompt no network error message on the screen. | no relevant error message is displyed on FE | Failed
2.1 | s17 | Verifty user sign up with all vaild credentials in online mode having low bandwidth. | s2 | Device is connected to network having low bandwidth. 1. User taps on full name input field and enters a valid full name. 2. User taps on email input field and enters a valid email address. 3. User taps on password input field and enters a valid password. 4. User taps the checkbox. 5. User taps on the signup button. | Full Name : neil conner Email : neilconner@gmail.com Password : testing123 | User should proceed with the signup process.
2.1 | s18 | Verifty user sign up with all vaild credentials in online mode having medium bandwidth. | s2 | Device is connected to network having normal/medium bandwidth. 1. User taps on full name input field and enters a valid full name. 2. User taps on email input field and enters a valid email address. 3. User taps on password input field and enters a valid password. 4. User taps the checkbox. 5. User taps on the signup button. | Full Name : neil conner Email : neilconner@gmail.com Password : testing123 | User should proceed with the signup process.
2.1 | s19 | Verifty user sign up with all vaild credentials in online mode having high bandwidth. | s2 | Device is connected to network having high bandwidth. 1. User taps on full name input field and enters a valid full name. 2. User taps on email input field and enters a valid email address. 3. User taps on password input field and enters a valid password. 4. User taps the checkbox. 5. User taps on the signup button. | Full Name : neil conner Email : neilconner@gmail.com Password : testing123 | User should proceed with the signup process.
2.1 | s20 | Verify data retention on the screen after minimizing the screen or switching the screen. | s2 | 1. User taps on full name input field and enters a valid full name. 2. User taps on email input field and enters a valid email address. 3. User taps on password input field and enters a valid password. 4. User taps the checkbox. 5. User minimizes the screen. | Full Name : neil conner Email : neilconner@gmail.com Password : testing123 | Data should remain in the fields.

## 03 - Login
Individual Login Testcases
Requirement ID # | Testcase # | Test Scenarios | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Status (19-feb)
2.4 | t1 | Availibility of application in both android and ios devices.
2.4 | t2 | Check if the application is running upon tap on the app icon. | App should be installed on the device. Should have a stable netword connectivity. | Tap on the app icon from the device |  | App should be functional | functional | Passed
2.4 | t3 | check if the login screen appears after when the app runs | t2 | Tap on the app icon from the device |  | Logn screen should be displayed on a device screen | login screen is displayed | Passed
2.4 | t4 | check if the login screen contains all the elements mentioned as per requirements. | t3 | Tap on the app icon from the device |  | Login screen should contains following elements : 1.Title "Individual Login" 2.Email field with icon, title and placeholder having text "Enter your email.". 3.Password field with icon, title and placeholder having text "Enter your password.". 4.Remember me check box. 5.Forgot your password link. 6.Social media icons. 7.Signup link. 8.Login button. | Login screen contains following elements : 1.Title "Individual Login" 2.Email field with icon, title and placeholder having text "Enter your email.". 3.Password field with icon, title and placeholder having text "Enter your password.". 4.Remember me check box. 5.Forgot your password link. 6.Social media icons. 7.Signup link. 8.Login button. | Passed
2.4 | t5 | check if the remember me feature is functional | t4 | 1. Click on the email field and enter a registered email address. 2. Click on the password field and enter a valid password. 3. Click on the remember me check box it should get checked. 4. Click on the login button. | Email : neilconner@gmail.com Password : Testing/123 | User should be able to login. User should be able to relogin without entereing username and password. | Remember me is not functional so far. | Failed
2.4 | t6 | check if the forgot your password link is functional | t4 | Click on the forgot password link. |  | It should be functional | Functional | Passed
2.4 | t7 | check if signup link is functional | t4 | click on the signup link |  | it should be functional | Functional | Passed
2.4 | t8 | check if authentication is functional with google account. | t4 | click on the google icon |  | user should be able to login via google account. | Not functional | Failed
2.4 | t9 | check if authentication is functional with facebook account. | t4 | click on the facebook icon |  | user should be able to login via facebook account. | Not functional | Failed
2.4 | t10 | check if authentication is functional with instagram account. | t4 | click on the intagram icon |  | user should be able to login via instagram account. | Not functional | Failed
2.4 | t11 | login with empty email and empty password | t4 | Leave the email field empty. Leave the password field empty. | Email : Password : | User should not be able to login. User should be shown error messages (as per requirement) | Error message prompted | Passed
2.4 | t12 | login with empty email and wrong password | t4 | Leave the email field empty. Tap on the password field and enter an invalid password. | Email : Password : T23423123 | User should not be able to login. User should be shown error messages (as per requirement) | Error message prompted | Passed
2.4 | t13 | login with empty email and valid password | t4 | Leave the email field empty. Tap on the password field and enter an valid password. | Email : Password : Testing/123 | User should not be able to login. User should be shown error messages (as per requirement) | Error message prompted | Passed
2.4 | t14 | login with wrong email and wrong password | t4 | Tap on the emaiil field and enter a invalid email. Tap on the password field and enter an invalid password. | Email : neilconnergmail.com Password : 12321/123 | User should not be able to login. User should be shown error messages (as per requirement) | Error message prompted | Passed
2.4 | t15 | login with valid email and wrong password | t4 | Tap on the emaiil field and enter a registered email.. Tap on the password field and enter an invalid password. | Email : neilconner@gmail.com Password : 2132/123 | User should not be able to login. User should be shown error messages (as per requirement) | Error message prompted | Passed
2.4 | t16 | login with valid email and valid password without remember me | t4 | Tap on the emaiil field and enter a registered email.. Tap on the password field and enter a valid password. | Email : neilconner@gmail.com Password : Testing/123 | User should be able to login. | unable to login and app prompts for checkin remember me | Failed
2.4 | t16 | login with valid email and valid password with remember me | t4 | Tap on the emaiil field and enter a registered email.. Tap on the password field and enter a valid password. | Email : neilconner@gmail.com Password : Testing/123 | User should be able to login. | User got loggedin | Passed
| Testcase # | Test Scenarios | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Status

## 04 - Forgot Password
Requirement ID # | Testcase # | Test Scenarios | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Status
2.5 | fp2 | check if the forgot password screen contains : title 'Enter your email.', a set of instructions an email field with title email, icon and placeholder enter your email and continue email button. | t6 (Login testcase) | User clicks on the forgot password ?, link | -- | Forgot password screen should appear to user containing following elements : 1. Title 'Enter your email'. 2. Instructions to user. 3. An Email Field containing Eamil as a title, an email icon, an input field with placeholder 'enter your email.' 4. Continue Email button.
2.5 | fp3 | verify that if user provides invalid email address. |  | 1. User taps on an email input field and enter an invaid email. 2. User clicks on the continue email button. | Email : asdfjkasdlf#com | It should prompt an error message 'Invalid email'
2.5 | fp4 | verifty that if user provides valid email but not registered | as above |  | Email : neilconnner1@gmail.com | It should prompt an error message 'Invalid email'
2.5 | fp5 | verify that if user provides valid email address which is already registered. | fp2 | 1. User taps on an email input field and enter with the registered email. 2. User clicks on the continue email button. | Email : neilconnner@gmail.com | 1. Send successful notification should appear. 2. OTP should be sent on the users registered email containing 5 digit code.
2.5 | fp6 | verfity that user should be able to receive email after providing a registered email address. | fp5 | User checks for expecting OPT code. |  | An email containing valid and working link to new password screen.
| fp7 | Verify that user should get redirect on the OTP verification screen. | fp6 | User taps on Continue Email. |  | OTP verificaiton screen should appear containing following screen elements : 1. A title "OTP Verification" 2. A text body. 3. Input field for accepting numeric values. 4. A timer field.
| fp8 | Verifty that app should prompt an error message incase of invalid OTP. | fp6 | User taps on the digit input field and enters a numeric values | OTP (invalid) : | App should prompt an error message
2.5 | fp9 | verifty that received email should contain a 5 digit OTP code. | fp6 , fp7 | -- |  | Email should contain a 5 digit numeric value.
| fp10 | Verifty that OTP should get expired after mentioned time peried. | fp6 , fp7 | -- |  | Should prompt an error message.
| fp11 | Verifty that previous OTP should not be working for new request. | fp5 ,fp6 , fp7 | -- | OTP (invalid) : | Should prompt an error message.
| fp12 | Verfity that OTP should be a unique and should be random number | fp6 | -- |  | Should not match with preious value and no pattern should get found.
| fp13 | Verifty that system should not validate the OTP code after expiration time. | fp6 , fp7 | User taps on the digit input field and enters a 5 digit numeric values after expiry time. | OTP : | Should prompt an error message.
| fp14 | Verifty that OTP field should only accept and validate numeric value. | fp7 | User taps on the digit input field and enters a 5 digit value. | OTP : | User should get redirected to the new password screen.
| fp15 | Verifty that OTP verification screen accepts the OTP code and OTP should be validate till expiry time. | fp7 | User taps on the digit input field and enters a 5 digit value. | OTP : | Should validate otp with in the expiry time.
2.5 | fp16 | Verifty that after validation of OTP user should be able to redirect on the enter new password screen. | fp7 , fp15 | User clicks on the resetpassword link. | Password : New Password : | New password screen should apppear to user having following elements : 1. Title 'Enter a new password' 2. An input field with heading Password. 3. An icon. 4. An input filed with placeholder 'Place new password.'
2.5 | fp17 | verify that user should be able to see error messages regarding invalid password reset. | fp8 | 1. User taps on a password input field and enter with the an invalid password. 2. User clicks on the Confirm passwird button. | Password : New Password : | It should prompt the set rules that are not matched for password.
2.5 | fp18 | verfity that user should be able to set a new password. | fp8 | 1. User taps on a password input field and enter a valid password. 2. User clicks on the Confirm passwird button. | Password : New Password : | New password should reset successfully. Successful message should prompt.
| fp19 | Verifty that user redirects on the success message screen. | fp18 | -- | -- | New screen appears with a tick mark logo and message on the screen "Your password changed successfully"
2.5 | fp20 | verify that user should not be abe to login wth the previous password. | fp18 , t6 (Login testcase) | 1. User taps on an email input field and enter a valid email. 2. User taps on a password input field and enter a new setted password. 3. User taps on login button. | Password : Previous/old Password : | User should remain on the login page. User should prompt with an error message stating "invalid password"
2.5 | fp21 | verify that user should be able to login with registed email and new password. | fp18 , t6 (Login testcase) | User be on the login as individual screen. 1. User taps on the email input filed and enters a valid email. 2. User taps on the password input field and enters a previous password. 3. User taps on the login button. | Password : New Password : | User should be able to access the home screen succussfully.

## 05 - Home Screen
Requirement ID # | Testcase # | Test Scenarios | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Status
2.8 | h1 | Accessability of Home screen after Successful login. | t16 (login testcase) |  |  | User should be able to successfully redirect to the Home screen.
2.8 | h2 | Visibility of components on the Home Screen. | h1 | User lands on Home screen |  | User should to able to view and have access to following features on the home screen : 1. Dashboard 2. Progress 3. Audio/Video Content 4. Pre Recorded Content 5. Prescheduled Live 6. Talk to Dia 7. Set Habit
2.8 | h3 | Verify that user is able to access Dashboard screen | h1 | User taps on the Dashboard navigation |  | User should be able to successfully navigate to the Dashboard screen.
2.8 | h4 | Verify that user is able to access Progress screen | h1 | User taps on the Progress navigation |  | User should be able to successfully navigate to the Progress screen.
2.8 | h5 | Verify that user is able to access Audio/video content | h1 | User taps on theAudio/video content navigation |  | User should be able to successfully navigate Video/Audio content screen.
2.8 | h6 | Verify that user is able to access Pre Recorded content | h1 | User taps on the Pre recorded content navigation. |  | User should be able to successfully navigate the pre recorded content screen.
2.8 | h7 | Verify that user is able to access Prescheduled live content | h1 | User taps on the Prescheduled live content navigation |  | User should be able to successfully navigate the prescheduled content screen.
2.8 | h8 | Verify that user is able to access Set habit screen from home. | h1 | User taps on the Set habit navigation |  | User should be able to successfully navigate to the Set habit screen.
2.9 | h9 | Verify that user is able to access chatbot, Talk to Dia, from home. | h1 | User taps on the chatbot navigation |  | User should be able to successfully navigate to the Talk to Dia chat feature..
| h10 | Verify that user is able to access Checkin screen from home. |  | User presses the check in option from home screen. |  | User should be able to successfully navigate to the Check In Screen.

## 06 - Dashboard
Requirement ID # | Testcase # | Test Scenarios | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Status
2.9 | d1 | Visibility of dashboard containing all the widgets and information as per requirements. | h3 (Home Screen testcase)
2.9 | d2 | Verify that user is shown with the video content on the screen. | d1 | User to be on Video/Audio content screen. |  | Video content that are uploaded by admin should be visibile to the user on the screen.
2.9 | d3 | Verify that user is shown with the audio content on the screen. | d2 | User to be on Video/Audio content screen. |  | Audio content that are uploaded by admin should be visibile to the user on the screen.
2.12 | d4 | Verify that user is shown with the prescheduled live video content | d3 | User to be on Prescheduled content screen. |  | Prescheduled content that are uploaded by admin should be visibile to the user on the screen.
2.11 | d5 | Verfiy that user should be able to play video content on the screen. | d4 | User taps on the video widget to play the video content. |  | User should be able to play the video content.
2.11 | d6 | Verfiy that user should be able to Pause/Stop video content on the screen. | d5 | User taps on the video widget to Pause/Stop the video content. |  | User should be able to Pause/Stop the video content.
2.11 | d7 | Verfiy that user should be able to play audio content on the screen. | d6 | User taps on the vido widgit to play the video content. |  | User should be able to play the Audio content.
2.11 | d8 | Verfiy that user should be able to Pause/Stop audio content on the screen. | d7 | User taps on the video widget to Pause/Stop the Audio content. |  | User should be able to Pause/Stop the Audio content.
2.11 | d9 | Verfiy that user should be able to play prescheduled content on the screen. | d8 |  |  | User should be able to play the Prescheduled content.
2.12 | d10 | Verfiy that user should be able to see the live tag on the screen for prescheduled content. | d9 | User on prescheduled video content. |  | Live tag should be displayed when prescheduled video is played on the screen.
2.9 | d11 | Verify that user should be able to leave the dashboard screen. | d10 | User taps on other naviagation. |  | User should not be on current screen. USer should navigate to the other screen as per tap.

## 08 - Focus Screen
Requirement ID # | Testcase # | Test Scenarios | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Status
| fs01 | Availability of focus screen with all the required widgets.
| fs02 | Verify if user can go back to home screen using back button.
| fs03 | Verify if user is able to move forward without selecting any interest.
| fs04 | verfity if user is able to select one or more and click on next button.
| fs05 | Verfity if user is able to see graph screen.
| fs06 | Verify if user is able to opt commited option.
| fs07 | Verfity if user is able to opt multiple commited options.
| fs08 | Verifty if user is able to select their daily schedule.
| fs09 | verifty if user is able to select thier weekly schedule.
| fs10 | verfity if user is able to set their notification.
| fs11 | verfity if user is able to save their focus.
| fs12 | Verify if user is shown with the animation screen.

## 09 - Checkin Screen
Requirement ID # | Testcase # | Test Scenarios | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Status
| cn1 | Availability of Check in screen as per requirements. | h10 (05 - Home Screen)
| cn2 | Verify if user can go back to home screen using back button.
| cn3 | Verify if user can See/Play/Pause animation on the screen.
| cn4 | Verify if user can choose the emoji's
| cn5 | Verfiy if user can choose multiple emoji's
| cn6 | Verfity if user can switch to next screen.

## 10 - Wisdom Screen
Requirement ID # | Testcase # | Test Scenarios | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Status
Availability of Check in screen as per requirements.
Verify if user can go back to home screen using back button.

## 11 - Progress Screen
Requirement ID # | Testcase # | Test Scenarios | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Status
Availability of Check in screen as per requirements.
Verify if user can go back to home screen using back button.

## 12 - Profile Screen
Requirement ID # | Testcase # | Test Scenarios | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Status
|  | Accessability of Profile screen . |  | User clicks on the profile option from home screen. |  | Profile screen should appear.
|  | Availability of Profile screen as per requirement/design. |  |  |  | Screen should be as per requirements/design.
|  | Verify if user can edit thier name. |  | user presses on the edit icon adjecent to name field. user type a name with updated name text. user presses on tick icon to save the new string. |  | Name should get updated.
|  | verify if user can avail free trails of premium account as per suggested time frame. |  | user presses on the free trail option on the profile screen. |  | User should succesfully get the premium content for the limited time.
|  | verify that the account gets expired after suggested time frame in case of free trail. |  |  |  | User should not be accessable to premium content after expiry date.
|  | verify if user can avail premium subscription as per defined method. |  | yet to be done. |  | User should access the premium content as per the flow.
|  | verify if user can cancel premium subscription. |  |  |  | user should successfully cancel the premium subscrption.
|  | verify if user can access change password option from profile. |  | User presses on the change password option. |  | user should successfully change the password.
|  | verify if user can access change email option from profile. |  | User presses on the change email option. |  | user should successfully change the email.
|  | verfiy if user can access help option from profile. |  | User presses on the change help option. |  | user should successfully access help content
verify if user can access notification settings from profile.
|  | verify if user can opt push notificaiton or email notification or both, from profile. |  | User presses on the push/email or both options. |  | user should receive the notificaitons as per opted option.
|  | verify if user can signout by pressing on logout icon from profile. |  | User presses on the logout option. |  | user should get logout.

## 13 - Dia
Requirement ID # | Testcase # | Test Scenarios | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Status
|  | Accessing dia chat screen. |  | User presses the dia icon from the home screen. |  | Chat with dia welcome screen should apprear
|  | Availability of dia start chat screen. |  |  |  | Screen containing followings : 1. Avatar 2. Greeting message with the name of the user. 3. start chat button.
|  | Verify if user have access to interact with dia chat bot. |  | User presses on start chat button from the screen. |  | Chatting screen should appear with a greeting message form chat bot.
|  | Verify if user can go to back screen. |  | User presses on the back arrow icon. |  | User should get back to the previous screen from the current one.
|  | Verify if user can select the predefied mood options that are displayed |  | user presses on the predefied moods |  | Chat bot should respond back to the user as per their selection.
|  | Verify if chat bot is responding to the user as per expectations. |  | user presses input test field and writes its query. user presses send button. |  | Chat bot should respond to the user aling to what is user is expecting.
|  | Verify if user can ask chat bot by typing the the text into the chat. |  | user presses input test field and writes its query. user presses send button. |  | Chat bot should responde to the user as per expectations.
|  | Verify if user can send the voice note. |  | user presses voice note icon. user speaks/shares the voice note. user presses on the send icon. |  | Chat bot should responde to the user as per expectations.
|  | Verify if user can access the change wallpaper screen to change the background img/color. |  | user presses on the change background icon. |  | Change background screen should appear
|  | Verify if user can choose the images/colors that are available on the screen. |  | user presses on the change background icon. user presses on the image/color from the change backgound screen. user presses on the set backgound button. |  | User should be able to select the option freely.
|  | Verify the change implemenation after choosing the imag/color. |  | user presses on the change background icon. user presses on the image/color from the change backgound screen. user presses on the set backgound button. |  | Changes should be implemented as per expectations.
|  | Verify if user can remove the background img/color from change wallpaper screen. |  | user presses on the change background icon. user presses on the delete icon on the image/color palet from change backgound screen. user presses on the set backgound button. |  | Background image/color should get removed.
|  | Verify if user can access any link/redirects if shared by chat bot. |  | user presses on the link/redirects shared by dia chat bot. |  | User should get redirected to the screen/resource after pressing on the link.
Verify if user sends invalid text
Verify if chat bot correctly identifies the users intents and responds accordingly.
Verify if the chatbot remembers previous interactions and responds contextually.

## Web- Super Admin testcases
Login
Sr # | Testcase # | Test Scenarios | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Status
| l1 | Availability of login page containing email/username input field, password input field and other elements as per requirements. | A valid application url. | Open a web browser and enter a valid url | Url : sdfs | User should be able to redirect on the Super Admin login panel. Login panel should contain - email/username input field, - password input field , - and other elements as per requirements. (will be list down later)
| l2 | Super admin login with empty email and empty password | l1 | Leave the email and password fields as empty. | Email : Password : | Should prompt an error message
| l3 | Super admin login with empty email and wrong password | l1 | Click on the password field and enter a randong string. | Email : Password : | Should prompt an error message
| l4 | Super admin login with empty email and valid password | l1 | Click on the password field and enter a randong string. | Email : Password : | Should prompt an error message
| l5 | Super admin login with wrong email and wrong password | l1 | 1. Click on the email field and enter a wrong email. 2. Click on the password field and enter a wrong password. | Email : Password : | Should prompt an error message
| l6 | Super admin login with valid email and empty password | l1 | Click on the email field and enter a registered email. | Email : Password : | Should prompt an error message
| l7 | Super admin login with valid email and wrong password | l1 | 1. Click on the email field and enter a valid email. 2. Click on the password field and enter a wrong password. | Email : Password : | Should prompt an error message
| l8 | Super admin login with valid email and valid password | l1 | 1. Click on the email field and enter a registered email. 2. Click on the password field and enter a valid password. | Email : Password : | User should be able to login successfully
| l9 | Verify that forgot password or reset password link is functional. | l1
Reset password
Sr # | Testcase # | Test Scenarios | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Status
| r1 | verify that if user provides invalid email address. |  | User clicks on the email input field and inputs an invalid email. clicks on the send button.
| r2 | verifty that if user provides a non registered email. |  | User clicks on the email input field and inputs an unregistered email. clicks on the send button.
| r3 | verify that if user provides valid and registered email address. |  | User clicks on the email input field and inputs a valid and registered email. clicks on the send button.
| r4 | verfity that user should be able to receive email after providing a registered email address. |  | User clicks on the email input field and inputs a valid and registered email. clicks on the send button.
| r5 | verifty that received email should contain reset password link and should be able to redirect the user to the reset password screen |  | User clicks on the link provided over an email.
| r6 | verfity that user should be able to see the enter your new password screen, containing password filed with title, icon , placeholder and button. |  | User clicks on the link provided over an email.
| r7 | verify that user should be able to see error messages regarding invalid password reset. |  | User clicks on the New password input field and enters an invalid new password. User clicks on the confirm password input field and enters a new password matching/not matching. User clicks on the save button.
| r8 | verfity that user should be able to set a new password. |  | User clicks on the New password input field and enters a valid new password. User clicks on the confirm password input field and enters a new password matching. User clicks on the save button.
| r9 | verify that user should be able to login with registed email and new password. |  | User clicks on the email field and enters a valid email. User clicks on the password field and enters a new password. User clicks on the login button.
| r10 | verifty that user should not be abe to login wth the previous password. |  | User clicks on the email field and enters a valid email. User clicks on the password field and enters an old password. User clicks on the login button.
| r11 | verifty that if user should not be sent with an email until first link is being used or expired.
User Management
Sr # | Testcase # | Test Scenarios | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Status
| u1 | Availability of User Management screen | l8 (Admin Login)
| u2 | Super Admin should be able to add user using add user button. | u1
| u3 | Super Admin should be able to view all the users that are already added. | u1
| u4 | Super Admin should be able to edit/update the users profile by clicking on the edit icon. | u1
| u5 | Super Admin should be able to delete a user profile. | u1
| u6 | Super Admin should be able to terminate a user. | u1
| u7 | Super Admin should be able to save the changes after changes. | u1
| u8 | Super Admin should be able to leave the screen. | u1
Content Management
Sr # | Testcase # | Test Scenarios | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Status
| c1 | Availability of Content Management module. | l8 (Admin Login)
| c2 | Super Admin should be able to access content management screen. | c1
| c3 | Super Admin should be able to Add Content | c1
| c4 | Super Admin should be able to Select Content | c1
| c5 | Super Admin should be able to Select Content Type | c1
| c6 | Super Admin should be able to View List of Content | c1
| c7 | Super Admin should be able to Edit/ Update Content Details | c1
| c8 | Super Admin should be able to Delete Content | c1
| c9 | Super Admin should be able to save the changes after changes. | c1
| c10 | Super Admin should be able to leave the screen. | c1
Habit Management
Sr # | Testcase # | Test Scenarios | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Status
| h1 | Availability of Habit Management module. | l8 (Admin Login)
| h2 | Super Admin should be able to access habit management screen. | h1
| h3 | Super Admin should be able to add a habit. | h1
| h4 | Super Admin should be able to Edit/Update a Habit | h1
| h5 | Super Admin should be able to Remove a Habit | h1
| h6 | Super Admin should be able to View the list of Habits | h1
| h7 | Super Admin should be able to save the changes after changes. | h1
| h8 | Super Admin should be able to leave the screen. | h1
Stats Management
Sr # | Testcase # | Test Scenarios | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Status
| s1 | Availability of Stats Management Module. | l8 (Admin Login)
| s2 | Super Admin should be able to add Habit. | s1
| s3 | Super Admin should be able to Edit/Update Habit. | s1,s2
| s4 | Super Admin should be able to Remove Habit. | s1
| s5 | Super Admin should be able to View the list of Habit. | s1
| s6 | Super Admin should be able to save the changes. | s1
| s7 | Super Admin should be able to leave the screen. | s1
Focus/Interest Management
Sr # | Testcase # | Test Scenarios | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Status
| f1 | Availability of Focus/Interest Management Module | l8 (Admin Login)
| f2 | Super Admin should be able to Access Focus/Interest Management screen. | f1
| f3 | Super Admin should be able to add Focus. | f1
| f4 | Super Admin should be able to Edit/Update Focus. | f1
| f5 | Super Admin should be able to Remove focus. | f1
| f6 | Super Admin should be able to View the list of focus. | f1
| f7 | Super Admin should be able to save the changes. | f1
| f8 | Super Admin should be able to leave the screen. | f1